## Sheet1
CELL FPC
EXEGER
|  | PROJECT STARTS | 2020-09-29
|  | Display Week | 1 |  | 2020-09-28 | [6 empty] | 2020-10-05 | [6 empty] | 2020-10-12 | [6 empty] | 2020-10-19 | [6 empty] | 2020-10-26 | [6 empty] | 2020-11-02 | [6 empty] | 2020-11-09 | [6 empty] | 2020-11-16 | [6 empty] | 2020-11-23 | [6 empty] | 2020-11-30 | [6 empty] | 2020-12-07 | [6 empty] | 2020-12-14
 | time axis 2020-09-28 to 2020-12-20
TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2020-09-28 to 2020-12-20
Shipping flex
Lead time normal FPC | Christian | 100% | 2020-10-18 | 2020-11-03
Lead time Flex Herpatech [Old design] | Anna/Björn | 50% | 2020-10-27 | 2020-11-03
Lead time Flex HerpaTech [new design] | Anna/Björn | 50% | 2020-10-06 | 2020-11-03
Mount Flex to Cell | FAB | 0% | 2020-11-03 | 2020-11-08
Test of cells | R&D | 0% | 2020-11-08 | 2020-11-12
Ship date | Nicklas | 10% | 2020-11-13 | 2020-11-13
Things that needs answers:
Do we need opening in flex from below?
*- Both for customer and fab
Do we need to tape the flec to the cell?
Soldering or pointwelding, Go for solder and continue research on welding?
Lead time, unprepared vs prepared
If HT, there will be no opening in flex, required to bend flex
Pre-tinned?
Reflow?
Test method? Estimated test time